## Report
OSINT Project
Earned Value Analysis Report
| Prepared By: | Saikrishna Gundeti
| Date: | 2024-04-30
[42]
For Period:
Summary:
This workbook holds the records for the entire project’s spending in order to maintain the budget.
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | TBC | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1.1 | Create a Project | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | Develop a process for collecting | 2525 | 50 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225
1.3 | Gather data | 515 | 20 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
1.4 | Create a limited prototype | 3002 | 1000 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182
1.5 | Develop a dashboard | 515 | 20 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
1.6 | Create a software program | 3504 | 600 | 264 | 264 | 264 | 264 | 264 | 264 | 264 | 264 | 264 | 264 | 264
| Create a report for analysis | 297 |  | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27
| Present report and findings | 253 |  | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23
| Management | 2500 | [11 empty] | 2500
0
0
0
Insert new rows above this one
| Total Budgeted Cost | 15611 | 4190 | 811 | 811 | 811 | 811 | 811 | 811 | 811 | 811 | 811 | 811 | 3311
|  | Cumulative Planned Value (PV) | 4190 | 5001 | 5812 | 6623 | 7434 | 8245 | 9056 | 9867 | 10678 | 11489 | 12300 | 15611
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 4000 | 4750 | 5025 | 6375 | 7200 | 8025 | 8850 | 9600 | 10500 | 11350 | 12150 | 15625
|  | Cumulative Earned Value (EV) | 3000 | 3750 | 4500 | 5025 | 5850 | 7000 | 8000 | 9000 | 10000 | 11000 | 12000 | 16000
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | -1000 | -1000 | -525 | -1350 | -1350 | -1025 | -850 | -600 | -500 | -350 | -150 | 375
|  | Schedule Variance (SV = EV - PV) | -1190 | -1251 | -1312 | -1598 | -1584 | -1245 | -1056 | -867 | -678 | -489 | -300 | 389
|  | Cost Performance Index (CPI = EV/AC) | 0.75 | 0.78947 | 0.89552 | 0.78824 | 0.8125 | 0.87227 | 0.90395 | 0.9375 | 0.95238 | 0.96916 | 0.98765 | 1.024
|  | Schedule Performance Index (SPI = EV/PV) | 0.71599 | 0.74985 | 0.77426 | 0.75872 | 0.78692 | 0.849 | 0.88339 | 0.91213 | 0.9365 | 0.95744 | 0.97561 | 1.0249
|  | Estimated Cost at Completion (EAC) | 20814.6667 | 19773.9333 | 17432.2833 | 19805 | 19213.5385 | 17896.8964 | 17269.6688 | 16651.7333 | 16391.55 | 16107.7136 | 15806.1375 | 15245.1172
Note on A21: Work Breakdown Structure (WBS)
Note on C21: Total Budgeted Cost (TBC)

## EV
Earned Value Worksheet
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP). | [14 empty] | Earned Value Management Template
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet. | [14 empty] | © 2012 Vertex42 LLC
Enter the % Complete for each task to calculate the cumulative earned value.
Cumulative Earned Value (EV)
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1.1 | Create a Project | 2500
1.2 | Develop a process for collecting | 2525
1.3 | Gather data | 515
1.4 | Create a limited prototype | 3002
1.5 | Develop a dashboard | 515
1.6 | Create a software program | 3504
- | Create a report for analysis | 297
- | Present report and findings | 253
- | Management | 2500
- | - | 0
- | - | 0
- | - | 0
Insert new rows above this one
|  | Cumulative EV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## AC
Actual Cost Worksheet
Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period.
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Transfer the Cumulative Actual Cost to the Report worksheet.
Actual Cost (AC) of Work Performed
WBS | Task Name |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1.1 | Create a Project
1.2 | Develop a process for collecting
1.3 | Gather data
1.4 | Create a limited prototype
1.5 | Develop a dashboard
1.6 | Create a software program
- | Create a report for analysis
- | Present report and findings
- | Management
- | -
- | -
- | -
Insert new rows above this one
|  | Total Actual Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cumulative Actual Cost (AC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0